## Sheet1
Predicted Raw Lines of Code/Hour | 20 |  | Predicted Code/Hour | 8.3333
Actual Raw Lines of Code / Hour | 18 |  | Actual Code/Hour | 12
Debugging Factor | 1.6
Learning Factor | 1.5
| Lines (Predicted) | Lines (New Predict) | Predicted Time (LPH) | Predicted Time (Adj) | New Estimate (LPH) | Predicted Time (Adj) | Recommendation
Admin Interface | 150 | 188.6667 | 18 | 15 | 15.7222 | 16 | Do
Dynamic Settings/Variables | 150 | 200 | 18 | 15 | 16.6667 | 17 | Do
Private Links | 150 | 116.6667 | 18 | 15 | 9.7222 | 10 | Do
Visually Pleasing GUI | 175 | 300 | 21 | 20 | 25 | 25 | Do
Secure Database | 175 | 350 | 21 | 20 | 29.1667 | 30 | Do
Q method Sorting | 270 | 175 | 32.4 | 30 | 14.5833 | 15 | Do
End of Survey Questionnaire | 50 | 150 | 6 | 5 | 12.5 | 10 | Do
Drag and Drop | 50 | 90 | 6 | 5 | 7.5 | 10 | Do
Manual Adjustment of Grid | - | 120 | - | - | 10 | 15 | Do
Editing Registration Page Fields (bonus) | - | 40 | - | - | 3.3333 | 5 | Drop
Clone Existing Survey as Template (bonus) | - | 100 | - | - | 8.3333 | 10 | Drop
Upload Statements from Txt (bonus) | - | 50 | - | - | 4.1667 | 5 | Do
Session Management for Users (bonus) | - | 160 | - | - | 13.3333 | 20 | Drop
Communication | - | - | 50 | 50 | 60 | 60 | Do
Documentation | - | - | 15 | 15 | 25 | 25 | Do
Learning |  |  | 30 | 30 | 30 | 30 | Do
Sum | 1170 | 1830.3333 | 205.4 | 190 | 255.0278 | 273 | 238
Whole Project Initial Estimate | 1500 |  | 125